Marketing Communications Plan (DRAFT#2)     7.1.17

Strengthening Working Families Initiative

“Access to Success”

Provided by a grant from:

In partnership with:







Prepared by the Communications and Marketing Department, Community College of Aurora, July 10, 2017.

Marketing Communications Plan Overview
The Communications and Marketing Department at the Community College of Aurora has developed this external plan to identify the marketing and communications strategies and tactics needed to promote the college’s federally funded program, “Access to Success”.

This plan incorporates feedback from the SWFI planning committee, which is comprised of partner organizations involved in the successful implementation of the SWFI grant. Additionally, we believe that the strategies and tactics in this plan will help meet the committee’s goals as prescribed by the grant and the target audience for which it serves.

The objectives of this marketing communications plan are to identify tactics to (1) help 
enhance visibility and awareness for the program and (2) to help staff recruit and enroll students for training that meets the goals of the SWFI program. This plan will be adjusted going forward to meet the goals and objectives set by the Department of Labor grant and the target audience.

The timeline for this plan will be for one year starting June 30, 2017 – July 1, 2018 and will be revised in subsequent years until the end of the grant funding.

CCA’s Strengthening Working Families Initiative (SWFI) Grant Program

History and Background

In July of 2016, the Community College of Aurora received a four-year $3.9 million grant from the U.S. Department of Labor as part of its Strengthening Working Families Initiative. The program, a public-private partnership between CCA and a host of community partners, also received a $1 million matching grant from Gary Community Investments, a local philanthropic organization in the metro Denver area.

The program provides education and training to help parents access jobs in three high-demand, high growth areas: healthcare, information technology, and advanced manufacturing. The program also helps mitigate the challenges parents may encounter by offering innovative case management and wrap-around services, access to quality childcare options, and employer engagement.

Through discussions with grant partners and additional information conducted by CCA, additional points became apparent that helped determine the high need for this program:

- In the Denver area, the IT, Healthcare, and Advanced Manufacturing sectors and occupations have large numbers of job openings, strong annual growth, and multiple career pathways.

- IT, Healthcare, and Advanced Manufacturing offer attainable entry with short-term academic or industry certification credentials.

- Existing training programs are not structured to provide childcare, system navigation skills and fast track, flexible programming to help parents obtain the skills and education credentials needed to advance.

- Programs have limited resources to address gaps in basic math and language skills that parents need to succeed in education and training.

- There are also limited numbers of accelerated certificate programs offering stackable academic and industry certification credentials.

Training programs also lack systems navigation and case management support to help participants identify and access childcare options and to troubleshoot academic challenges on the way to job placement and career advancement success. The “Access to Success” program helps with these challenges as well.

CCA anticipates close to 800 students and families will be served throughout the grant cycle. In addition, 200 participants will be served annually in technical training programs, including: IT Tech & Support/Computer Technology, Certified Nursing Assistant, Medical Office Specialist and Medical Administrative Assistant, machining and welding certificates.

The Program Mission

The mission of the Strengthening Working Families Initiative is to define the expectations of parents as students in the educational system by supporting the students academically and guiding them to a better career and/or job, which in effect will lead to strengthening the parents and their families.

SWFI Program Goals

Overall Program Goals

The main priority for the Strengthening Families program is to provide the support and guidance that non-traditional students need to become successful in an educational system. The program not only focuses on getting students into college but also focuses on their success by providing resources that make navigating the academic, campus life and workforce, more accessible.

Enrollment Goals

- Remainder of Fiscal Year 1 (July 1, 2016 – June 30, 2017) - To enroll 33 students for the summer semester.

- Fiscal Years 2 through 4 (2017-2020) – To enroll 178 student per fiscal year.

Target Audience
The target audience for this program is parents age 17-40 with a high school diploma or equivalent; a child 13 years or younger and a U.S. citizen. The audience is responsible for their future education, training, childcare, and employment. They may/may not live in the Aurora area near CCA, but has access to classes at both CCA campuses and the Community College of Denver’s campus.

The Competition

Career training programs that lead to a certificate are very prevalent in the service area from where we draw our target market to this program. In the metro Denver area, two community colleges offer similar programs. Arapahoe Community College of Front Range Community College offer a variety certificate programs in the areas of IT, healthcare, and advanced manufacturing. However, these certificate programs do not offer childcare or comprehensive career/job placement services.

The SWFI program is unique in that it addresses barriers families face to childcare and provides students with comprehensive wrap around support services, including childcare, which promotes academic success and job placement.

Strengths, Weaknesses, Opportunities, and Threats
Several strengths, weaknesses, opportunities, and threats associated with this program.

| STRENGTHS | Short term training and education programs designed to provide access to in demand career fields: IT, Healthcare and Advanced Manufacturing | OPPORTUNITIES | To create programming changes that address the needs of parents and access to quality education and childcare services. |
| --- | --- | --- | --- |
|  | Comprehensive wrap around support services, including childcare, which promotes academic success and job placement. |  | To lift families out of poverty and promote long-term independence with sustainable solutions. |
|  | Collective impact of strategic relationship that includes educational, childcare, retention, and employer partners |  | To promote the benefits of ROI models for child care, while increasing capacity within the community. |
|  | Program fills many gaps for parents needing to develop a plan to provide for their families. |  | To provide a pathway for education beyond the certificate and career advancement. |
| WEAKNESSES | Low enrollment numbers for first year of grant. | THREATS | Failure to meet grant outcomes if enrollment numbers do not increase at a rate of 35 students per month. |
|  | Student engagement and registration commitment from SWFI application to enrollment. |  | Ensuring processes are scalable. As we look ahead at serving potentially 200 or more students at a time, our processes must be able to accommodate 200-300 students with existing personnel. |
|  | Marketing of the program is managed with handouts and networking within organization. However, there is a need for a more robust marketing and promotional plan. |  | Processes that are external to the education institutions that can have an adverse effect on the grant outcomes, such as licensing procedures by the state. |

Program Partners
A strength of the SWFI program is its collaboration with a variety of external partners that will engage with students to help them achieve their academic success and job placement.

| Partner | Service Provided | Description |
| --- | --- | --- |
| Gary Community Investment* | Matching funds | Addresses barriers to childcare and promote childcare capacity within the community by creating programming and systemic changes. |
| Community College of Denver* | Educational Partner | Provides additional education and training programs. |
| Worklife Partnership* | Employment Retention | Provides retention and up-skilling support to participants upon employment and engage with employers on childcare ROI models. |
| Partner | Service Provided | Description |
| Early Childhood Partnership of Adams County* | Childcare | Provides childcare navigation support. |
| Denver Office of Economic Development | Outreach | Promotes SWFI program internally to assist with recruitment goals. |
| Arapahoe/Douglas Works | Outreach | Promotes SWFI program internally to assist with recruitment goals. |
| University of Colorado Health, Children’s Hospital of Colorado, Colorado Advance Manufacturing Alliance | Employment | Provides job preparedness support. |
| Colorado Office of Early Childhood | Childcare | Provides childcare support. |
| Colorado Department of Human Services | Childcare | Provides childcare support and navigation. |
| Community –Campus Partners |  |  |

*partners funded through the SWFI grant

Brand Positioning and Messaging
A weakness of the SWFI program the staff has identified is that it lacks an identity with the target market. It is important for the staff and its partners to agree upon a central message that conveys the brand’s promise so that the potential students can begin to identify with the brand.

BRAND AWARENESS
Brand awareness involves the consumers’ ability to recall and/or recognize the brand, logos, and advertising. The brand helps consumers differentiate competing brands and helps them determine which brand satisfies their needs. Brand awareness is key to a purchasing decision or call to action. One key element of a successful brand is its high level of brand awareness. Due to a successful brand awareness campaign that CCA launched in 2015-2016, potential and current students are engaging with the Potential Realized brand. The campaign for the Entrepreneurship and Small Business Management Program will augment the Potential Realized brand to further instill in the consumers’ minds that being a successful business owner means realizing their potential.

To increase enrollment, potential students must engage with the program through brand awareness. The goal here is to engage the target audiences with strong messaging that creates top-of-mind awareness and a call to action that will entice them to enroll when they are thinking about seeking a career in business or becoming a business owner. Brand awareness involves the brand positioning statement, brand message, and the brand promise.

Suggested Brand Positioning Statement for SWFI:

For parents with children, SWFI provides training to help them enter the workforce for economic stability and community.

Brand Message

Brand messaging supports the brand positioning statement. Below are two suggested brand messages for the SWFI program. Staff and planning committee will choose one.

Strengthening Working Families

Your Family. Your Career. Your Future.

Strengthening Working Families

Get the Training. Get the Job. Change Your Future.

Brand Promise
The brand promise is essential to the brand positioning statement and must be met at the front line of product/service delivery. Below are three brand promises for the SWFI program:

- A program that can help parents become students who achieve long term economic sustainability for their families through education, training and support for starting and building a career.

- A program that strengthens families, communities, and the workforce through training and education.

- Expanding Access to Education + Child Care = Economic Success.

Marketing Communications Plan

This plan incorporates feedback from the SWFI planning committee, which is comprised of partner organizations involved in the successful implementation of the SWFI grant. Additionally, we believe that the strategies and tactics in this plan will help meet the committee’s goals as prescribed by the grant and the target audience for which it serves. The timeline for this plan will be for one year starting June 30, 2017 – July 1, 2018 and will be revised in subsequent years until the end of the grant funding.

The goal of this plan is to identify and support the marketing communications needs of the SWFI program grant as implemented by the Community College of Aurora and its partners.

The objective of this marketing communications plan are to identify tactics to help staff increase enrollment for the SWFI program through increased awareness and visibility. This plan will be adjusted going forward to meet the goals and objectives set by the Department of Labor grant and the target audience.

The strategy is to create memorable messages and images that resonate with the primary target audience to meet the objectives of this plan.

The tactics we will use to communicate with the target audience include:

- Collateral Materials

- Earned Media

- Paid Media

- Community Outreach and Events

- Internet and Newsletters

Target Audiences
The primary target audience for this program is low-income parents age 17-40 with a high school diploma or equivalent; a child 13 years or younger and a U.S. citizen. The audience is responsible for their future education, training, childcare, and employment. They may/may not live in the Aurora area near CCA, but has access to classes at both CCA campuses and the Community College of Denver’s campus.

The secondary target audience is community partners/service providers and the community at large who can be influencers on the primary target audience.

The Competition

Career training programs that lead to a certificate are very prevalent in the service area from where we draw our target market to this program. Two community colleges in the Denver area offer similar programs. Arapahoe Community College of Front Range Community College offer a variety certificate programs in the areas of IT, healthcare, and advanced manufacturing. However, these certificate programs do not offer childcare or comprehensive career/job placement services.

Uniqueness

The SWFI program is unique in that it addresses barriers families face to childcare and provides students with comprehensive wrap-around support services, including childcare, which promotes academic success and job placement.

Marketing Communications Tactics

Currently students learn about the SWFI program through partner networks, outreach from schools, other students, local community organizations, and word-of-mouth.

We have identified the following tactics for the program that we believe will provide the most reach and cost-effectiveness. Additionally, while we realize this can be a grassroots effort, some tactics may be more appropriate than others to reach the target audience. Materials will be provided to the program’s partners to also use through their channels of communication to further deliver the program messaging.

- Collateral Materials

  - Flyers (general awareness)

  - Brochure (general awareness)

  - PowerPoint template

  - Pull-up Banners (general awareness)

  - Direct Mail (sent two times per year/Fall and Spring) – these may also include grade schools and middle schools within the target market.

- Earned Media

  - Media relations

    - Send the most appropriate and relevant press releases to media contacts.

    - Identify stories that resonate with the media and prospective students (success stories, general awareness, events, milestones).

    - Identify talk show hosts that may be interested in our story.

    - Include Spanish-language broadcast and print media outlets.

  - Social Media
We will use the college’s existing social media accounts to post relevant messages that resonate with the target audience. Consistent, frequent posting across all identified social media platforms is suggested in order to reach the target audience and to optimize content.

    - Facebook (incl. social media usage data using unique URL)

    - Twitter (incl. data)

    - YouTube (include short video with hashtag #SWFI)

SWFI partners will be asked to share messaging on their respective social media channels in order to expand coverage.

  - Video
In order for the primary audience to engage with the brand, we must evoke emotion and tell stories that resonate with them. We will create one video that features a SWFI family in the program or a successful graduate. The video can be used to promote the program outside of the college and other shorter videos can be created for future use on earned media and paid media outlets. The video can also be used at recruitment events and general community meetings and events where appropriate.

- Community Outreach and Events
Identify opportunities to present the SWFI program to the larger community.

Community meetings and organizations:

    - Aurora Chamber of Commerce

    - Aurora Communities of Faith

    - Meetings with Employers and other community organizations

    - City Council Meetings

Community events:
Below are some suggested community events. The SWFI outreach coordinator, the planning committee, and others may have a list of more relevant events where the SWFI program can be promoted.

- City of Aurora Global Fest (Aug. 19, 2017)

- Ethiopian Festival (TBC – August)

- Central American Festival (TBC – September)

- Paid Media

Identify cost-effective media strategies that will garner the most reach to the target audiences. We will work with our current advertising agency/media buyer to identify the media schedule and appropriate campaign timeline.

- Out of Home 
(extremely cost-effective method with high reach and can be geographically targeted)

  - Transit advertising (bus tails or kings)

  - Radio

    - Pandora ads (targeted to audience with unique URL to track users; also include Spanish-language ads)

- Print Advertising 
(provides efficient reach, opportunity for repeat advertising exposure, and more detailed copy/messages – only if appropriate)

  - Ads in ethnic community papers (e.g. LaVoz, Urban Spectrum, 
El Seminario, LaPrensa)

  - Ads in local papers (Aurora Sentinel)

- Search Engine Optimization - identify best usage of online search engines to reach target audiences.

  - Google AdWords

  - Google, Bing

- Interactive/Digital 
(provides general awareness, allows for performance measurement)

  - Targeted email messaging

  - Facebook advertising

  - Video – produce a general awareness video about the program, which can be used during presentations or on social media channels.

- Internet and Newsletters

  - Information about the SWFI program exists as a webpage on the CCA and CCD websites.

    - Visitors to the CCA website can either search on the toolbar or by using the link: https://www.ccaurora.edu/strengthening-working-families

    - Visitors to the CCD website can access the information.

Timeline (tentative)

The timeline for this plan will be for one year starting June 30, 2017 – July 1, 2018 and will be revised in subsequent years until the end of the grant funding.

| Tactic | Timing | Responsible | Notes |
| --- | --- | --- | --- |
| Approval for marketing communications plan. | July 13 | Mary Meeks, Victor V. |  |
| Social media: - Develop and implement a social media posting calendar | June, July, August |  |  |
| Paid Advertising: Identify paid advertising media schedule to include digital, radio, and transit. | July-August (4 weeks) |  |  |
| Design, approve, and print collateral materials. Produce radio commercial for approval. | July 7 | Mary Meeks + graphic designer |  |
| Video: Identify students to interview and begin concept, interviews and production. |  |  | Target completion date: July 15 |
| Media Relations: - Identify news stories and pitch to appropriate reporters | June - July |  | Topics can include: |
| Identify and attend community meetings. | June, July, August | SWFI Outreach Coordinator | Collect attendance data for each event. |
| Determine which community events to attend and secure payment for table/booth. | July | SWFI Outreach Coordinator |  |
| Registration messaging. | July- August |  |  |
| Advertising Placements (TBC) | July - August |  |  |
| Tactic | Timing | Responsible | Notes |
| Website | Ongoing | CCA, CCD web content staff |  |
| Direct mail #1 | October 2017 |  |  |
| Direct mail #2 | May 2018 |  |  |

Budget Estimates
The categories below are budget estimates only. Exact dollars depend on length and scope of the advertising campaign. The program can provide additional dollars to support the budget if needed.

Collateral Materials

Design				$2,000.00

Printing			$5,000.00

- brochures

- flyers

- direct mail

- pull-up banners

- posters

Advertising				$15,000.00

Transit

Radio

Print

Digital

Production			       	 $ 2,000.00

Estimated Budget			$24,000.00

Measurement

We will rely on advertising campaign analytics, such as Google Analytics, to determine impressions and exposure by target audience as one measurement of program awareness.

We will also rely on enrollment data supplied by the SWFI program staff, comparing enrollment prior to marketing communications campaign and then afterwards. This information will also indicate whether the overall program goals for enrollment were achieved and will show how this plan affected those outcomes.